ALDRIDGE FINANCIAL TECHNOLOGIES

ISO/IEC 27001:2022 Gap Analysis — Findings

Certification readiness assessment prepared for the Executive Risk Committee

| Document reference | AFT-ISMS-GAP-01 | Version | 2.0 |
| --- | --- | --- | --- |
| Document owner | Head of Security Governance | Approved by | Chief Information Security Officer |
| Effective date | 9 September 2026 | Next review | On completion of P1 remediation |
| Classification | Confidential | Applies to | Executive Risk Committee |

## Contents

Contents	2

1. Executive summary	3

2. Assessment position	3

3. Principal findings	4

3.1 The management system does not exist	4

3.2 The apex policy is missing	4

3.3 Scope integrity is compromised by unmanaged software as a service	4

3.4 Third-party assurance has lapsed	4

3.5 Detection coverage is uneven between the two platforms	5

3.6 Retention is published but not enforced	5

3.7 The residual uncodified estate	5

4. What is working	5

4A. Obligations outside the ISO scope	6

5. Remediation approach	6

5A. Effort, cost and deliverability	7

6. Assessment of the certification timetable	7

7. Recommendations	8

8. Basis and limitations	9

9. Related documents	9

# 1. Executive summary

Aldridge Financial Technologies commissioned this assessment to establish its readiness for ISO/IEC 27001:2022 certification, with a Stage 1 audit targeted for the second quarter of 2027. The assessment covered all 93 Annex A controls and the management system requirements at clauses 4 to 10.

The finding is straightforward and, in one respect, encouraging. Aldridge operates a materially stronger set of security controls than most organisations at this stage of a certification programme. Half of the Annex A control set is implemented at a certifiable maturity, and several domains — identity and access management, privileged access, vulnerability management, network segregation and incident response — are strong by any standard. That is the dividend of five years of PCI DSS Level 1 compliance and three annual SOC 2 audits.

The problem lies elsewhere. ISO/IEC 27001 does not certify a control set. It certifies a management system, defined at clauses 4 to 10, and Annex A is a reference list of controls that the management system selects from. Aldridge has the controls and does not have the management system. Of the twenty-five clause requirements assessed, one is met.

This is the central conclusion of the assessment, and it has a direct consequence for the timetable. The remediation effort is not primarily a security engineering effort; it is a governance and documentation effort, and much of it must be performed in sequence rather than in parallel.

# 2. Assessment position

| Measure | Result | Population | Comment |
| --- | --- | --- | --- |
| Annex A controls implemented at maturity 3 or above | 46 | 92 applicable | A 50% conformance rate; respectable at this stage |
| Annex A controls partially implemented | 43 | 92 applicable | Most sit at maturity 2 — working in practice, not formalised |
| Annex A controls not implemented | 3 | 92 applicable | A.5.7, A.5.21, A.8.34 |
| Annex A controls not applicable | 1 | 93 total | A.8.30 outsourced development — justification required in the SoA |
| Clause 4–10 requirements met | 1 | 25 assessed | Only clause 7.1 Resources |
| Total gaps raised | 70 | — | 46 Annex A, 24 clause |
| Gaps at P1 (audit-readiness prerequisites) | 17 | 70 | 14 of the 17 are clause gaps |

Gap distribution by Annex A theme shows where the weakness concentrates. Organisational controls have a 59% gap rate; technological controls 50%; physical 36%; people 25%. That pattern is the signature of an engineering-led security function operating without a governance layer.

# 3. Principal findings

## 3.1 The management system does not exist

Every foundational requirement of the standard is absent or incomplete. There is no approved scope statement, no documented risk assessment methodology, no risk treatment plan, no Statement of Applicability beyond an unreviewed draft, no information security objectives, no ISMS internal audit programme, and no management review. Risk is tracked in a spreadsheet maintained by one person.

This matters more than the count of clause gaps suggests, because these requirements are mutually dependent. The scope statement cannot be approved until the asset inventory is complete. The risk assessment cannot be performed until the methodology is defined and the scope is fixed. The Statement of Applicability cannot be completed until the risk assessment has produced treatment decisions. The internal audit cannot be conducted until the ISMS it audits is operating. The management review cannot occur until the internal audit has produced results to review.

That chain is the critical path of the entire programme, and it is roughly nine months long irrespective of how many people are assigned to it.

## 3.2 The apex policy is missing

The four Tier 2 policies reviewed — acceptable use, incident response, access control, and data classification — are of good quality, current, and cross-referenced. However AFT-ISMS-POL-05, the Tier 1 Information Security Policy required by clause 5.2, has never been written. There is therefore no document that establishes the ISMS, states information security objectives, commits to satisfying applicable requirements, or commits to continual improvement.

This is a small piece of work with a large consequence. It is a certain major nonconformity if left unaddressed, and it should be the first item completed.

## 3.3 Scope integrity is compromised by unmanaged software as a service

Cloud infrastructure governance is strong. Software-as-a-service governance is not. Approximately forty applications identified by the cloud access security broker in August 2026 are in use without registration, owner, classification, contract or assessment. Until those applications are triaged, the company cannot state with confidence what falls inside the ISMS scope, cannot complete the asset inventory, and cannot perform a risk assessment that would withstand audit.

This single issue blocks three separate clause requirements. It is the highest-value item outside the management system build itself.

## 3.4 Third-party assurance has lapsed

The third-party risk process is defined and applied at onboarding, but reassessment is not being performed. Eleven of thirty-four Tier 1 and Tier 2 suppliers are overdue. Northgate Analytics, which sits in the synchronous payment authorisation path and receives Restricted data, was last assessed in October 2024 — twenty-three months ago. Eight suppliers, Northgate among them, are on pre-2023 contracts that do not carry the current security schedule.

There is also no visibility of the onward supply chain. Aldridge cannot presently identify the subcontractors used by its own suppliers, which means it cannot answer where Restricted data ultimately resides. Auditors ask this question, and so increasingly do enterprise customers.

## 3.5 Detection coverage is uneven between the two platforms

Logging, monitoring and detection content are mature for Aldridge Pay and the cardholder data environment, and thin for Aldridge Credit. Approximately 15% of the Credit servicing estate does not ship logs to the SIEM at all. Those systems hold Restricted borrower data. An incident affecting them could not be reconstructed from central evidence.

The disparity has an obvious cause: PCI DSS drove investment into the Pay estate and there has been no equivalent external pressure on the Credit estate. ISO/IEC 27001 does not permit that distinction, since both are in scope.

## 3.6 Retention is published but not enforced

The Records Retention Schedule is a sound document that is not technically implemented. Identifiable borrower data persists in the analytics warehouse beyond its stated retention period. This is a nonconformity against A.5.33, A.5.34 and A.8.10, and separately it is a breach of the UK GDPR storage limitation principle carrying its own regulatory exposure independent of the certification programme.

This finding should be escalated to the Data Protection Officer for assessment on its own merits, not held within the certification workstream.

## 3.7 The residual uncodified estate

Approximately 20% of the Aldridge Pay estate is not managed through infrastructure as code. Those components sit inside the cardholder data environment, permit manual change, are not subject to drift detection, and cannot produce a complete change history. The same components are implicated in findings against configuration management, change management, software installation control and cryptographic key ownership.

One remediation — codifying that estate — closes four separate gaps. It is the highest-leverage technical item in the plan.

# 4. What is working

A gap analysis that reports only deficiencies gives management a distorted picture and makes it harder to judge where investment is genuinely needed. The following areas were assessed as strong and require no remediation.

- Identity and access management. Universal multi-factor authentication, phishing-resistant credentials for privileged access, just-in-time elevation through a privileged access management platform, no standing production privilege, and evidenced recertification at quarterly and monthly cadence. This is above the standard typically seen at this company size.

- Incident response. Documented lifecycle, four-tier severity model, named commanders with deputies, an external forensics retainer, and two tabletop exercises completed during 2026 including one with executive participation.

- Vulnerability management. Cloud and container scanning, software composition analysis in the pipeline, defined remediation service levels that are met, and evidenced tracking.

- Network segregation. Cardholder data environment, secure data zone, production, non-production, corporate and guest networks isolated in separate accounts, validated annually by the qualified security assessor.

- Environment separation and secure coding. Separate accounts with no network path between them; static analysis enforced in the pipeline with blocking thresholds.

# 4A. Obligations outside the ISO scope

One matter falls outside the assessment brief and is recorded because omitting it would leave a misleading impression of the compliance position.

Aldridge is a money services business licensed in forty-four states, operating under a sponsor bank arrangement, with an FCA-authorised subsidiary. It therefore carries Bank Secrecy Act programme obligations, OFAC sanctions screening obligations on a strict liability basis, suspicious activity reporting obligations that extend to cyber-events, customer identification programme obligations, and the UK Money Laundering Regulations. It is also subject to NYDFS Part 500, which requires a cybersecurity programme, a risk assessment, 72-hour event notification, and an annual certification signed by the Chief Information Security Officer.

None of these obligations has an Annex A equivalent, and an ISMS scope statement does not discharge any of them. Two specific exposures were identified in passing and have been raised as risks rather than as ISO gaps:

- The incident response policy notification matrix did not include FinCEN suspicious activity reporting or NYDFS Part 500, and no route existed connecting an incident to the financial crime function for assessment. A cyber-event meeting the reporting threshold would have been handled as a security matter only. This has been corrected in POL-02 v3.1.

- The NYDFS Part 500 annual CISO certification requires, among other things, a documented risk assessment. On the position found at this assessment, that certification could not have been given truthfully. This is recorded as risk R-51.

The wider financial crime programme was not assessed and is outside our competence to assess on this engagement. We recommend that it receive an equivalent independent review, and note that the overlap between financial crime controls and information security controls is substantial enough that assessing either in isolation understates the exposure.

# 5. Remediation approach

The accompanying workbook organises all seventy gaps into eleven workstreams with named leads. The sequencing constraint set out at 3.1 means the programme cannot simply be parallelised across those workstreams, and the plan should be run in three phases.

| Phase | Period | Content | Exit criterion |
| --- | --- | --- | --- |
| Phase 1 — Foundations | Oct 2026 – Jan 2027 | Apex policy; context, interested parties and scope; risk methodology; SaaS triage and asset inventory completion; risk assessment performed; Statement of Applicability approved; objectives set | SoA approved and risk treatment plan signed by risk owners |
| Phase 2 — Control remediation | Jan 2027 – Apr 2027 | The P2 Annex A work: supplier backlog, logging coverage, retention enforcement, key inventory, threat modelling, DR exercise, configuration codification, awareness programme | All P2 gaps closed with evidence retained |
| Phase 3 — Operate and assure | Apr 2027 – Sep 2027 | ISMS operates and generates records; internal audit performed; management review held; corrective actions raised and closed; P3 items addressed | Internal audit report and management review minutes exist |

# 5A. Effort, cost and deliverability

The remediation plan carries an estimate of 914 internal person-days and approximately USD 461,000 of external spend, excluding the certification body fee. At a blended internal rate the indicative total is in the region of USD 1.28m. These are planning estimates at the accuracy available before detailed scoping, and should be treated as an order of magnitude rather than a budget.

The more consequential figure is the capacity analysis. Effort assigned to the three heaviest workstream leads is between 149% and 166% of the working days available to them before the Phase 2 deadline, and all three hold substantial business-as-usual responsibilities on top of it. The plan as assigned is not deliverable, and no amount of programme discipline will make it so.

The choice is therefore explicit: appoint a dedicated ISMS manager and reassign workstreams away from the overloaded leads, or move the timetable. Approving the plan without resolving this is how certification programmes slip six months without anyone having decided that they should, and it is the single most likely cause of failure for this programme.

# 6. Assessment of the certification timetable

The Executive Risk Committee approved a Stage 1 target of the second quarter of 2027. On the evidence of this assessment, that target is achievable for Stage 1 and is not achievable for Stage 2 in the same year without a compressed and, in our view, unrealistic assumption about how quickly an ISMS can generate evidence of operation.

Stage 1 is a documentation and readiness review. If Phase 1 completes on schedule, the auditor will find an approved scope, a documented methodology, a completed risk assessment, an approved Statement of Applicability and a risk treatment plan. That is what Stage 1 examines, and it is deliverable by June 2027.

Stage 2 examines whether the management system is operating effectively, and that requires records. Clause 9.2 requires a completed internal audit of the ISMS. Clause 9.3 requires a management review that considers, among other inputs, those audit results. Clauses 8.2 and 8.3 require evidence that risk assessment and treatment have been performed as planned rather than merely designed. None of that can be produced in advance; it accrues over elapsed time. Certification bodies generally look for at least three months of operating records, and in a regulated financial services context an auditor is likely to want more.

We therefore recommend that the Executive Risk Committee re-baseline to Stage 1 in Q2 2027 and Stage 2 in Q4 2027, and that any customer commitments made on the strength of the current timetable be reviewed against that revised position. Committing externally to certification within 2027 H1 would create a risk of a failed Stage 2 or of a deferred audit, either of which is more damaging commercially than a realistic date set now.

# 7. Recommendations

| # | Recommendation | Owner | By |
| --- | --- | --- | --- |
| 1 | Draft and approve AFT-ISMS-POL-05 Information Security Policy at Tier 1, signed by the Chief Executive. Smallest item on the list, and a certain nonconformity if omitted. | Helen Achebe-Ward | 31 Oct 2026 |
| 1a | Approve the Statement of Applicability (AFT-ISMS-SOA-01), now complete and issued unsigned, following completion of the SaaS triage on which the scope statement depends. | Executive Risk Committee | 31 Jan 2027 |
| 1b | Obtain risk owner approval on the Risk Treatment Plan. All 55 signature blocks are currently unsigned, and clause 6.1.3(f) is not satisfied until they are. | Chidi Eze | 31 Jan 2027 |
| 2 | Appoint a dedicated ISMS manager for the duration of the programme. The clause 4–10 build is roughly nine months of sequenced work and cannot be absorbed alongside existing governance duties. | Helen Achebe-Ward | 31 Oct 2026 |
| 3 | Complete the SaaS triage and close the asset inventory. This gates scope approval, which gates the risk assessment. | Claire Bennett | 30 Nov 2026 |
| 4 | Define the risk assessment methodology and perform the first full assessment, producing the risk treatment plan and Statement of Applicability. | Chidi Eze | 31 Jan 2027 |
| 5 | Escalate the retention overage to the Data Protection Officer for independent assessment as a potential UK GDPR compliance matter, separate from the certification programme. | Sofia Kallio | 30 Sep 2026 |
| 6 | Clear the supplier reassessment backlog, Tier 1 first, beginning with Northgate Analytics. | Elena Petrova | 31 Jan 2027 |
| 7 | Procure GRC tooling. Five uncontrolled spreadsheets will not survive Stage 2, and the evidence burden grows through Phase 3. | Chidi Eze | 31 Dec 2026 |
| 8 | Re-baseline the certification timetable to Stage 1 in Q2 2027 and Stage 2 in Q4 2027, and review external commitments accordingly. | Executive Risk Committee | 31 Oct 2026 |
| 9 | Resolve the capacity position at section 5A: either appoint a dedicated ISMS manager and reassign workstreams, or move the timetable. Do not approve the plan without deciding this. | Executive Risk Committee | 31 Oct 2026 |
| 10 | Commission an equivalent independent review of the financial crime programme, and consider whether information security and financial crime assurance should in future be planned together given the overlap. | Jonathan Reyes | 31 Dec 2026 |

# 8. Basis and limitations

- The assessment was performed through document review, control walkthroughs, system inspection and interview during September 2026.

- No independent testing of operating effectiveness was performed. Where a control is recorded as implemented, that reflects design adequacy and the evidence presented, not an audit opinion. Column F of the control register records the specific evidence reviewed for each assessment, and column H distinguishes design from operating deficiency where the two differ.

- Maturity ratings are assessed against the scale in AFT-CTX-01 section 8.2. Maturity 3 is treated as the minimum certifiable level.

- The assessment reflects the position as at 9 September 2026 and should be refreshed on completion of Phase 1.

- This document is not an audit report and confers no assurance opinion. It is an internal readiness assessment prepared to inform the certification programme.

# 9. Related documents

- AFT-CTX-01 — Organisation Context Pack v1.0

- AFT-ISMS-GAP-01 — ISO/IEC 27001:2022 Gap Analysis workbook (accompanies this memo)

- AFT-ISMS-SOA-01 — Statement of Applicability v1.0, complete and unsigned (supersedes draft v0.3)

- AFT-ISMS-POL-01 to POL-04 — issued Tier 2 policies

- AFT-ISMS-RSK-01 — Information Security Risk Register v2.0, with Risk Treatment Plan

- AFT-TPRM-ASM-01 — Third-Party Risk Assessment v2.0