## Cover & Method
Information Security Risk Assessment
Aldridge Financial Technologies ¦ AFT-ISMS-RSK-01 ¦ Version 2.0 ¦ 9 September 2026 ¦ Classification: Confidential
CHANGES IN VERSION 2.0
Register expanded from 30 to 55 risks following expert review. Twenty-five risks added covering financial crime (sanctions, AML, SAR filing, CIP), single-cloud concentration, supplier financial viability and fourth-party concentration, fraud and settlement loss, data subject rights, and specific regulatory exposures including the NYDFS Part 500 CISO certification.
Every risk now names a threat source from the AFT-CTX-01 section 14 threat profile, and every likelihood estimate now carries a stated evidence base. A Risk Treatment Plan with risk owner sign-off has been added to satisfy clause 6.1.3(e) and (f), which version 1.0 did not.
FRAMEWORK POSITION — READ THIS FIRST
Conducted under NIST SP 800-30 Rev. 1 using FIPS 199 for security categorisation. It operates within the Prepare, Categorize and Select steps of the NIST Risk Management Framework (SP 800-37 Rev. 2). It is NOT a full RMF implementation.
RMF is a seven-step federal system authorisation lifecycle concluding with an Authorizing Official granting an Authorization to Operate. Aldridge has no Authorizing Official, no ATO and no federal system. The Implement, Assess, Authorize and Monitor steps as defined in SP 800-37 do not apply and have not been performed. Describing this as 'an RMF risk assessment' without that qualification would not be defensible.
A NOTE ON INHERENT RISK
This assessment scores inherent risk (the exposure assuming the control environment is absent) alongside residual risk. The approach is contested: some practitioners hold that inherent risk is not meaningfully estimable, since one cannot coherently imagine this organisation operating with no access control at all. It is used here for two reasons: it makes control contribution visible, which supports investment decisions; and it exposes controls that reduce nothing, as at R-05 and R-41 where inherent and residual are equal because the control is ineffective. Where the inherent estimate is weak, the residual figure governs.
SCOPE AND BASIS
Scope | The 22 information assets catalogued in AFT-CTX-01 section 4, and the regulatory obligations at section 1.2.
Method | Asset-based assessment. Threat sources per AFT-CTX-01 section 14. Vulnerabilities drawn from AFT-ISMS-GAP-01 and from inspection.
Inputs | AFT-CTX-01 v2.0; AFT-ISMS-GAP-01 v2.0; AFT-TPRM-ASM-01 v2.0; incident history 2024-2026; obligations register.
Interval | At least annually and on significant change, once clause 8.2 is established.
SCALES
Impact 1-5 | 1 Negligible (<USD 50k) · 2 Minor (50k-500k) · 3 Moderate (500k-2m, reportable breach) · 4 Major (2m-10m, formal regulatory finding) · 5 Severe (>10m, licence or authorisation at risk)
Likelihood 1-5 | 1 Rare (<1 in 10 years) · 2 Unlikely (1 in 3-10 years) · 3 Possible (1 in 1-3 years) · 4 Likely (once in 12 months) · 5 Almost certain (more than once in 12 months, or already occurring)
Rating | Critical 16-25 (Board Audit Committee) · High 10-15 (ERC) · Moderate 5-9 (CISO) · Low 1-4 (asset owner)
Control effectiveness | Strong (reduces likelihood two bands or more) · Effective (one band) · Limited (less than one band) · Ineffective (no reduction; inherent equals residual)
LIMITATIONS
Likelihood estimates are judgement-based and informed by the evidence stated in the Likelihood basis column; they are not actuarial. Impact values use the financial and regulatory anchors in AFT-CTX-01 and have not been separately modelled. No control testing was performed; effectiveness ratings are carried from AFT-ISMS-GAP-01. Risks arising from the approximately 40 unregistered applications are represented in aggregate at R-04, R-45 and R-47 and cannot be individually assessed until that inventory closes. R-40 carries an unsupported likelihood by design: no supplier financial assessment has ever been performed, and recording a placeholder is more honest than implying an estimate exists.

## System Categorisation
FIPS 199 Security Categorisation
Impact level per security objective. Overall category is the high-water mark, per FIPS 199 s3.
ID | Asset | Owner | Information types | Confidentiality | Integrity | Availability | Overall | Rationale
A-01 | Aldridge Pay transaction processing service | Oliver Trent | Cardholder data; payment transaction records; merchant identifiers | High | High | High | High | Authorisation path for USD 14.2bn annualised volume. Loss of integrity permits fraudulent settlement; loss of availability halts merchant revenue across 2,400 platform customers.
A-02 | Cardholder data vault (tokenisation) | Oliver Trent | Cardholder data; tokenisation key material | High | High | High | High | Compromise would expose account data at scale and trigger payment brand and state notification. Detokenisation failure halts all card processing.
A-03 | Aldridge Credit origination platform | Amara Diallo | Borrower personal data; credit decision data; bank account details | High | High | Moderate | High | Holds identifiers and credit files. Integrity loss produces erroneous or unfair lending decisions with fair-lending exposure.
A-04 | Aldridge Credit servicing and collections | Amara Diallo | Borrower personal data; repayment and arrears records; bank details | High | High | Moderate | High | Integrity loss misstates borrower obligations and creates consumer harm and regulatory exposure.
A-05 | Borrower credit file store (secure data zone) | Amara Diallo | Credit files; government identifiers; income and affordability data | High | High | Moderate | High | The most sensitive concentration of personal data in the estate.
A-06 | Aldridge Ledger reconciliation API | Marcus Lindqvist | Transaction and settlement records; merchant balances | Moderate | High | Moderate | High | Integrity is paramount: reconciliation errors propagate into customer settlement and financial reporting.
A-07 | Customer portal and merchant dashboard | Amara Diallo | Merchant account data; transaction summaries; user credentials | Moderate | Moderate | Moderate | Moderate | Principal customer interface. Presents data held authoritatively elsewhere.
A-08 | Public marketing website | Nadia Haddad | Public marketing content; enquiry form submissions | Low | Moderate | Low | Moderate | No sensitive data. Integrity matters: defacement or injected content would damage trust and could be used to phish customers.
A-09 | Snowflake analytics warehouse | Claire Bennett | Aggregated borrower and transaction data; identifiable data beyond retention | High | Moderate | Low | High | Confidentiality is High because identifiable borrower data persists here contrary to SCH-01 (W-09).
A-10 | Fraud decisioning integration | Oliver Trent | Transaction metadata; truncated cardholder data; risk scores | High | High | High | High | Synchronous in the authorisation path and dependent on an external Tier 1 supplier (V-01).
A-11 | Okta identity provider | Ruth Nakamura | Authentication credentials; identity and entitlement data | High | High | High | High | Compromise confers access to every federated system. Unavailability locks out the entire workforce.
A-12 | HashiCorp Vault secrets store | Sanjay Mehta | Credentials; API keys; cryptographic key material | High | High | High | High | Concentrates the secrets protecting every other asset.
A-13 | GitHub source code repositories | Marcus Lindqvist | Proprietary source code; infrastructure definitions; CI configuration | Moderate | High | Moderate | High | Integrity is High: malicious commits reach production through the pipeline.
A-14 | CI/CD pipeline and deployment tooling | Sanjay Mehta | Deployment credentials; build artefacts; release records | Moderate | High | Moderate | High | A compromised pipeline is a direct path to production regardless of other controls.
A-15 | AWS management and organisation accounts | Sanjay Mehta | Cloud configuration; organisation policy; root credentials | High | High | High | High | Control-plane compromise is equivalent to compromise of every asset it governs.
A-16 | Splunk SIEM and log archive | Tomas Vidal | Security event data; audit trails; investigation records | Moderate | High | Moderate | High | Integrity is High: log tampering would defeat detection and destroy evidential value.
A-17 | Google Workspace (mail, drive, docs) | Grace Lindberg | Business correspondence; Confidential documents; contracts | Moderate | Moderate | Moderate | Moderate | Broad but generally not Restricted content. Principal phishing target.
A-18 | HR information system | Grace Lindberg | Employee personal data; contracts; performance records | Moderate | Moderate | Low | Moderate | Personal data of 610 workers. Authoritative source for joiner, mover and leaver automation.
A-19 | Finance and ERP system | Daniel Okonkwo | Financial records; supplier bank details; payment instructions | Moderate | High | Low | High | Integrity is High: payment instruction manipulation is a direct fraud route.
A-20 | Corporate endpoints (610 devices) | Ruth Nakamura | Cached Confidential data; credentials; local working files | Moderate | Moderate | Low | Moderate | Distributed exposure. Mitigated by encryption, EDR and prohibition on local Restricted storage.
A-21 | Austin office and comms room | Grace Lindberg | Physical documents; network equipment; visitor records | Low | Low | Moderate | Moderate | No production processing on premises. Comms room supports site connectivity.
A-22 | London office (landlord-managed access) | Grace Lindberg | Physical documents; workstations | Low | Low | Low | Low | No production processing. Access administration outside Aldridge control (W-11).

## Risk Register
Information Security Risk Register
55 risks. Scores, ratings, appetite test and approval level are formulas. Threat sources per AFT-CTX-01 s14.
Risk ID | Risk | Assets | TA | Threat source | Appetite category | Threat event | Vulnerability / condition | Existing controls | Inh. I | Inh. L | Inh. score | Inh. rating | Likelihood basis | Control effectiveness | Res. I | Res. L | Res. score | Res. rating | Max tolerable | Appetite test | Treatment | Risk owner | Target date | Approval to accept
R-01 | Ransomware encrypts production estate and backups | A-01, A-02, A-03, A-04, A-15 | TA-01 | Organised criminal group | Service availability | Deployment of ransomware following initial access, with attempted destruction of backups before encryption | Cross-region failover has not been exercised end to end since March 2025, so the one-hour recovery objectives are unproven (W-07). | CrowdStrike EDR across endpoints and servers; network segregation into separate accounts; immutable cross-region backups; universal MFA; just-in-time privileged access with no standing production privilege; 24/7 SOC. | 5 | 4 | 20 | Critical | Sector incident data: ransomware remains the most frequently reported cause of material disruption in financial services. No Aldridge incident to date. Inherent L4 reflects sector frequency; residual L2 reflects tested EDR and segregation. | Effective | 5 | 2 | 10 | High | 9 | EXCEEDS | Treat | Sanjay Mehta | 31 Mar 2027 | Executive Risk Committee
R-02 | Compromise of cloud control-plane credentials | A-15, A-11, A-12 | TA-08 | Sophisticated external attacker | Data confidentiality | Theft or misuse of organisation-level AWS credentials granting estate-wide access | Concentration of authority in the management accounts; break-glass credentials exist by necessity. | Root and organisation-owner credentials under dual custody with hardware tokens; CyberArk just-in-time elevation, four-hour maximum; privileged access workstations mandatory; break-glass sealed, alerted on every use and reconciled within one business day; session recording retained 12 months. | 5 | 4 | 20 | Critical | No Aldridge occurrence. Inherent L4 reflects the frequency of cloud credential compromise in published breach reporting. Residual L1 reflects dual custody and the absence of standing privilege. | Strong | 5 | 1 | 5 | Moderate | 9 | Within | Tolerate | Sanjay Mehta | n/a | CISO
R-03 | Cardholder data exfiltrated from the cardholder data environment | A-02, A-01 | TA-01 | Organised criminal group | Data confidentiality | Extraction of stored account data following compromise of a CDE component | The CDE remains a high-value target notwithstanding tokenisation. | Tokenisation of stored account data; field-level encryption with customer-managed keys; network segregation validated annually by the QSA; DLP tuned to cardholder data patterns; monthly access recertification; comprehensive logging to Splunk. | 5 | 3 | 15 | High | No Aldridge occurrence in five years of PCI operation. Residual L1 supported by annual QSA validation of segmentation. | Strong | 5 | 1 | 5 | Moderate | 9 | Within | Tolerate | Oliver Trent | n/a | CISO
R-04 | Borrower personal data exposed through unregistered software as a service | A-05, A-09, A-17 | TA-10 | Worker (non-malicious) | Data confidentiality | Upload or synchronisation of Restricted or Confidential data to an unassessed third-party application | Approximately 40 SaaS applications are in use without registration, owner, classification, contract or assessment (W-04). Web filtering blocks malicious destinations but not unsanctioned services (A.8.23). DLP does not cover these channels (A.8.12). | POL-01 section 3.6 prohibits unapproved services; CASB provides discovery but not inline enforcement; annual awareness training. | 4 | 4 | 16 | Critical | Condition present: CASB discovery in August 2026 identified approximately 40 applications. L4 inherent reflects that the behaviour is occurring; residual L3 reflects partial detection without prevention. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Claire Bennett | 30 Nov 2026 | Executive Risk Committee
R-05 | Identifiable borrower data retained beyond its lawful retention period | A-09, A-05 | TA-10 | Internal process failure | Regulatory compliance | Continued storage of identifiable personal data after the purpose for processing has been fulfilled | SCH-01 is published but not technically enforced. No automated deletion at end of retention. The condition is present and ongoing, not prospective (W-09). | Records Retention Schedule published; legal hold process operated by the General Counsel; access control and encryption applied to the data at rest. | 4 | 5 | 20 | Critical | Condition present and confirmed by inspection of the Snowflake estate. L5 is not an estimate; the non-compliance exists. | Ineffective | 4 | 5 | 20 | Critical | 9 | EXCEEDS | Treat | Claire Bennett | 31 Mar 2027 | Board Audit Committee
R-06 | Malicious activity in Aldridge Credit servicing goes undetected | A-04, A-05 | TA-05 | External attacker or malicious insider | Data confidentiality | Unauthorised access to or manipulation of borrower servicing data that is neither detected nor reconstructable | Approximately 15% of the Credit servicing estate does not ship logs to Splunk (W-10). Detection content for that estate is thin and unmapped to any threat framework. | Perimeter and identity controls apply equally to this estate; EDR deployed; access recertification quarterly. | 4 | 4 | 16 | Critical | Internal: 15% logging gap confirmed by reconciliation of the asset register to Splunk sources. No detection means occurrence cannot be excluded. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Tomas Vidal | 31 Jan 2027 | Executive Risk Committee
R-07 | Compromise of Northgate Analytics exposes data in the authorisation path | A-10, A-01 | TA-06 | External attacker via supplier | Data confidentiality | Breach of a Tier 1 supplier receiving Restricted data synchronously during payment authorisation | Last assessed October 2024, twenty-three months ago (W-08). Contract predates 2023 and lacks the current security schedule, including the 24-hour notification obligation. Subcontractors are undisclosed (A.5.21). | Data shared is truncated and tokenised where possible; mutually authenticated integration; network path restricted; supplier holds a current SOC 2 report from 2024. | 5 | 4 | 20 | Critical | Sector data on third-party breach frequency, adjusted upward for a supplier unassessed for 23 months with no notification obligation. | Limited | 5 | 3 | 15 | High | 9 | EXCEEDS | Treat | Elena Petrova | 31 Jan 2027 | Executive Risk Committee
R-08 | Northgate Analytics outage suspends payment authorisation | A-10, A-01 | TA-10 | Supplier failure | Third-party concentration | Loss of the fraud decisioning service during trading hours | Single supplier in a synchronous critical path with no assessed alternative. No documented exit plan, contrary to the risk appetite statement for Tier 1 concentration. | Rules-based fallback scoring engaged automatically on supplier timeout, with tightened velocity limits while active; contractual availability commitment; status monitoring with alerting. | 5 | 3 | 15 | High | Supplier availability history: two degradations in 24 months, both under 30 minutes, both absorbed by the fallback engine. | Effective | 4 | 2 | 8 | Moderate | 15 | Within | Treat | Oliver Trent | 30 Jun 2027 | CISO
R-09 | Restricted data resides with undisclosed fourth parties | A-05, A-10 | TA-06 | Supplier subcontracting | Regulatory compliance | Onward transfer of Aldridge data to subcontractors that have not been identified, assessed or contractually bound | No subcontractor disclosure requirement in the questionnaire or in contracts. Aldridge cannot state where Restricted data ultimately resides, including whether it leaves the UK or US (A.5.21). | First-tier contracts include confidentiality terms; UK transfers governed by documented mechanisms for known flows only. | 3 | 4 | 12 | High | Condition present: the chain is unmapped, so onward transfer cannot be excluded and is likely given standard SaaS architecture. | Ineffective | 3 | 4 | 12 | High | 9 | EXCEEDS | Treat | Elena Petrova | 31 Mar 2027 | Executive Risk Committee
R-10 | Offshore support agent exfiltrates customer data | A-04, A-07 | TA-05 | Malicious insider at supplier | Data confidentiality | Bulk copying or photography of customer records by a Meridian BPO agent during dispute handling | Human access to Confidential data, with Restricted access on escalation, from a jurisdiction where Aldridge has no direct oversight. DLP does not extend to the supplier's environment. | Access limited to named agents through a dedicated time-bound path; activity logged; contractual background screening obligation; access scoped to the case in hand. | 4 | 3 | 12 | High | No Aldridge occurrence. Sector data on BPO insider incidents; adjusted for the volume of agents with Confidential access and the absence of DLP in the supplier environment. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Elena Petrova | 31 Mar 2027 | Executive Risk Committee
R-11 | Worker credentials phished and used for account takeover | A-11, A-17 | TA-04 | External attacker | Data confidentiality | Credential harvesting through a targeted phishing campaign, followed by authenticated access | 610 workers reachable by email. Most recent simulation click rate 14.2% with 4.6% credential submission. | Universal MFA; phishing-resistant FIDO2 for all privileged access; SMS one-time passcodes not accepted for privileged access; mail filtering; Report Phishing button with 31% report rate and 11-minute median first report; conditional access on device posture. | 4 | 5 | 20 | Critical | Internal: 14.2% simulation click rate and 4.6% credential submission across 610 workers, four campaigns per year. L5 inherent is directly evidenced. | Strong | 3 | 2 | 6 | Moderate | 9 | Within | Tolerate | Ruth Nakamura | n/a | CISO
R-12 | Untrained population raises susceptibility to social engineering | A-17, A-20 | TA-04 | External attacker | Data confidentiality | Successful manipulation of a worker who has not completed security training | Training completion is 91%, with the residual 9% concentrated in Sales and the London office (W-14). Forty-seven repeat clickers have received no targeted intervention (W-15). | Annual training platform in place; induction training required before access is granted; quarterly phishing simulation. | 3 | 4 | 12 | High | Internal: 91% training completion; 47 repeat clickers across the last four campaigns. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Helen Achebe-Ward | 31 Mar 2027 | CISO
R-13 | Unrecorded change to a cardholder data environment component | A-01, A-02 | TA-10 | Worker (non-malicious) or malicious insider | Regulatory compliance | Manual configuration change to a CDE component that is neither approved nor recorded | Approximately 20% of the Aldridge Pay estate sits outside Terraform, permits manual change, has no drift detection, and cannot produce a complete change history (W-12). | Change Advisory Board meets twice weekly; automated change records for the codified estate; privileged access brokered and session-recorded; PCI DSS change requirements applied. | 4 | 4 | 16 | Critical | Internal: change records could not be reconciled to deployment events for the uncodified estate; occurrence cannot be excluded. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Sanjay Mehta | 31 Mar 2027 | Executive Risk Committee
R-14 | Cryptographic key of unclear ownership cannot be rotated during an incident | A-02, A-12 | TA-10 | Internal process failure | Data confidentiality | Inability to rotate or revoke a compromised key because its owner, dependencies and blast radius are unknown | The key inventory is incomplete and ownership of several legacy Aldridge Pay keys is unclear (W-16). Rotation for those keys cannot be evidenced. | STD-09 Cryptographic Key Management Standard issued; KMS and Vault provide technical rotation capability; keys protected by access control. | 4 | 3 | 12 | High | Internal: key inventory incomplete; rotation for the affected keys has never been evidenced. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Sanjay Mehta | 31 Mar 2027 | Executive Risk Committee
R-15 | Disaster recovery fails to meet stated recovery objectives | A-01, A-02, A-03, A-04, A-11, A-12 | TA-10 | Infrastructure failure or regional outage | Service availability | Loss of an AWS region with failover that does not complete within the stated objective | Cross-region failover has not been exercised end to end since March 2025. Full restore of the Credit servicing estate has never been performed (W-07). | Multi-availability-zone deployment; cross-region replication configured; automated encrypted backups; component-level failover tested quarterly with results recorded. | 5 | 3 | 15 | High | Internal: no end-to-end failover exercise since March 2025. Likelihood reflects the probability of a triggering event combined with the probability that untested failover underperforms. | Limited | 5 | 3 | 15 | High | 9 | EXCEEDS | Treat | Sanjay Mehta | 31 Mar 2027 | Executive Risk Committee
R-16 | Identifiable production data present in non-production environments | A-05, A-03 | TA-10 | Internal process failure | Data confidentiality | Copying of identifiable borrower data into development or test environments held to a lower control standard | Standing exceptions permit production data in test. They are not consistently time-bound or reviewed, and use of the masking pipeline is not enforced at the account boundary (W-06). | POL-04 section 6.3 prohibits the practice; masking and tokenisation pipeline available; environments separated into distinct AWS accounts. | 4 | 4 | 16 | Critical | Internal: standing exceptions exist and are in use; identifiable data confirmed present in a non-production account. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Amara Diallo | 31 Mar 2027 | Executive Risk Committee
R-17 | Design-level security flaw reaches production undetected | A-01, A-03, A-07 | TA-10 | Internal process failure | Change and innovation | A vulnerability arising from architectural design rather than implementation passes through testing into production | The secure development lifecycle has no threat modelling stage, so design flaws are not systematically identified (W-06). Secure engineering principles are applied by convention but undocumented. | Mandatory peer review; SAST, DAST and SCA enforced in CI with blocking thresholds; annual external penetration test; architecture review for significant changes. | 4 | 3 | 12 | High | Internal: no threat modelling stage. Sector data indicates a material share of exploited vulnerabilities originate in design rather than implementation. | Effective | 3 | 3 | 9 | Moderate | 15 | Within | Treat | Marcus Lindqvist | 31 Mar 2027 | CISO
R-18 | ISO 27001 certification is delayed or fails, costing enterprise revenue | Commercial | TA-10 | Programme failure | Regulatory compliance | Stage 2 assessment not passed within the committed timeframe, causing loss of contracts conditional on certification | The management system does not yet exist: 24 of 25 clause requirements are unmet. Clause 9.2 and 9.3 evidence accrues only over elapsed time and cannot be compressed. | Certification programme approved and funded by the ERC; gap analysis complete; remediation plan defined across 11 workstreams. | 3 | 4 | 12 | High | Internal: 24 of 25 clause requirements unmet with a nine-month sequenced critical path against a Q2 2027 Stage 1 target. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Helen Achebe-Ward | 31 Jan 2027 | CISO
R-19 | PCI DSS compliance is not sustained at the next assessment | A-01, A-02 | TA-10 | Internal process failure | Regulatory compliance | Loss of Level 1 service provider compliance at the assessment preceding AOC expiry in April 2027 | The uncodified 20% of the Pay estate sits inside the CDE and cannot evidence a complete change history (W-12). | Mature PCI programme with five years of continuous compliance; annual QSA assessment; segmentation validated annually; comprehensive CDE logging; monthly access recertification. | 5 | 2 | 10 | High | Internal: five consecutive years of compliance; no adverse QSA findings. L2 inherent, L1 residual. | Strong | 4 | 1 | 4 | Low | 9 | Within | Tolerate | Oliver Trent | n/a | Asset owner
R-20 | Distributed denial of service degrades customer-facing services | A-01, A-07 | TA-07 | Hacktivist or extortion actor | Service availability | Volumetric or application-layer attack against public endpoints | Public endpoints are necessarily internet-facing. | AWS Shield and CloudFront edge absorption; WAF with rate limiting; autoscaling; runbook and tabletop coverage for volumetric attack. | 4 | 3 | 12 | High | Sector data on DDoS frequency against payment platforms. No Aldridge occurrence above edge absorption capacity. | Strong | 3 | 2 | 6 | Moderate | 9 | Within | Tolerate | Sanjay Mehta | n/a | CISO
R-21 | Payment fraud through compromised merchant credentials | A-01, A-07 | TA-02 | Organised criminal group | Regulatory compliance | Fraudulent transaction submission using stolen merchant portal credentials | Merchant credential hygiene is outside Aldridge control. Fraud detection depends on a Tier 1 supplier (see R-07, R-08). | Fraud decisioning on every authorisation; velocity and value limits; MFA available and enforced for merchant administrators; anomaly alerting to the risk team; chargeback monitoring. | 4 | 4 | 16 | Critical | Internal: merchant credential compromise observed at low volume in 2025 and 2026; contained by fraud decisioning. | Effective | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Oliver Trent | 30 Jun 2027 | CISO
R-22 | Credit decisioning model produces erroneous or unfair outcomes | A-03, A-05 | TA-10 | Internal process failure | Regulatory compliance | Model drift or defective training data yields decisions that are inaccurate or discriminatory in effect | Model governance is maturing. Fair-lending exposure in the US and consumer duty exposure in the UK. | Model validation before deployment; performance and drift monitoring; adverse action reason codes; human review of declines above threshold; periodic disparate impact testing. | 4 | 3 | 12 | High | No Aldridge occurrence. Likelihood reflects model drift frequency and the maturity of validation and monitoring. | Effective | 3 | 2 | 6 | Moderate | 9 | Within | Tolerate | Amara Diallo | n/a | CISO
R-23 | Proprietary source code exfiltrated | A-13 | TA-05 | Departing worker or external attacker | Data confidentiality | Bulk cloning of repositories to a personal or external destination | 230 engineers hold repository access. Cloning is a legitimate daily activity, so malicious cloning is hard to distinguish. | GitHub access by team with quarterly recertification; POL-01 prohibits pushing to personal repositories; four-hour leaver revocation; audit logging of repository access. | 3 | 3 | 9 | Moderate | No Aldridge occurrence. Sector data on departing-employee code exfiltration; adjusted for 230 engineers with legitimate cloning rights. | Effective | 3 | 2 | 6 | Moderate | 9 | Within | Tolerate | Marcus Lindqvist | n/a | CISO
R-24 | Compromised software dependency introduces malicious code | A-13, A-14 | TA-06 | Supply chain attacker | Change and innovation | A poisoned open source package or compromised upstream maintainer reaches production through the build | Substantial dependency surface across Go, TypeScript and Python. Fourth-party visibility is absent generally (see R-09). | Software composition analysis in CI with blocking thresholds; automated dependency upgrade pull requests; required review and signed commits; immutable build artefacts. | 4 | 3 | 12 | High | Sector data: dependency compromise events are now regular occurrences across major package ecosystems. | Effective | 3 | 3 | 9 | Moderate | 15 | Within | Treat | Marcus Lindqvist | 30 Jun 2027 | CISO
R-25 | CI/CD pipeline compromise enables unauthorised deployment to production | A-14, A-01 | TA-08 | Sophisticated external attacker | Change and innovation | Injection of a malicious artefact or workflow reaching production without human review | Approximately 40 deployments per day; the pipeline is a standing path to production by design. | OIDC federation with no long-lived deployment credentials; required reviews and CODEOWNERS enforcement; separate accounts per environment with no network path; artefact signing; deployment records generated automatically. | 5 | 2 | 10 | High | No occurrence. L2 reflects the strength of OIDC federation and required review; the pipeline remains a standing path to production. | Strong | 4 | 2 | 8 | Moderate | 15 | Within | Tolerate | Sanjay Mehta | n/a | CISO
R-26 | London office access cannot be revoked on termination | A-22 | TA-05 | Departing worker | Data confidentiality | Continued physical access to the London premises after the effective leaving date | Access credentials are issued and administered by the building landlord. Aldridge cannot produce a holder list, cannot revoke directly, and receives no entry logs (W-11). | Logical access revoked within four hours regardless of physical access; no production processing on premises; Confidential material subject to clear desk requirements. | 3 | 4 | 12 | High | Internal: revocation depends on a landlord request with no confirmed service level; occurrence probable on any given termination. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Grace Lindberg | 30 Jun 2027 | CISO
R-27 | Loss of the individual holding the risk and compliance record | ISMS | TA-10 | Key person dependency | Regulatory compliance | Departure or unavailability of the single worker who maintains risk, exception and compliance records | Risk, exceptions, policies and access review evidence are held across five uncontrolled spreadsheets maintained by the Head of Security Governance. No version control, approval record or retention rule (W-13). | Files held in corporate cloud storage with backup; the ERC receives periodic reporting derived from them. | 3 | 3 | 9 | Moderate | Single individual maintains the records; departure probability over a 12-month horizon. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Chidi Eze | 31 Dec 2026 | CISO
R-28 | Regulatory change outpaces compliance capability | Group | TA-10 | External regulatory change | Regulatory compliance | New or amended obligations across 44 state licences, FCA rules or payment brand requirements are not implemented in time | Broad and fragmented obligation surface across two jurisdictions and multiple regimes. | Obligations register maintained by Legal and reviewed quarterly; external counsel in both jurisdictions; trade association membership; PCI future-dated requirements tracked. | 3 | 3 | 9 | Moderate | Regulatory change frequency across 44 state regimes, FCA and PCI future-dated requirements. | Effective | 2 | 3 | 6 | Moderate | 9 | Within | Tolerate | Jonathan Reyes | n/a | CISO
R-29 | Targeted intrusion by a well-resourced adversary | A-01, A-02, A-05, A-15 | TA-08 | Organised criminal group or state-aligned actor | Data confidentiality | Sustained, targeted campaign against a payments and lending platform, using techniques selected to evade current detection | No formal threat intelligence capability: intelligence is a by-product of tooling, with no defined requirements, analysis or dissemination (W-05). Detection content is not mapped to a threat framework, so coverage cannot be measured (A.8.16). | EDR with 98% coverage; 24/7 SOC; network segregation; phishing-resistant privileged authentication; comprehensive logging for the Pay estate; annual penetration testing. | 5 | 3 | 15 | High | Sector targeting data for payments and lending platforms. L3 inherent reflects intent and capability; residual L2 reflects detection strength for the Pay estate only. | Effective | 5 | 2 | 10 | High | 9 | EXCEEDS | Treat | Tomas Vidal | 31 Mar 2027 | Executive Risk Committee
R-30 | Confidential data leaves through endpoint channels not covered by prevention | A-20, A-17 | TA-05 | Worker (non-malicious) or departing worker | Data confidentiality | Copying of Confidential material to removable media, personal cloud sync or personal webmail | DLP covers corporate mail and drive sharing but not endpoint channels, Snowflake query egress, or the unregistered SaaS estate (A.8.12). | Removable media restricted by device management and blocked for personal devices; automatic external mail forwarding blocked; POL-01 prohibits forwarding to personal accounts; endpoint encryption. | 3 | 3 | 9 | Moderate | Internal: DLP coverage gap confirmed; endpoint channel activity is not monitored, so occurrence cannot be excluded. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Tomas Vidal | 30 Jun 2027 | CISO
R-31 | Sanctioned party onboarded as a merchant or borrower | A-01, A-03 | TA-09 | Sanctions evader (TA-09) | Regulatory compliance | Onboarding of an entity or individual subject to OFAC or UK sanctions, or processing a payment on their behalf | US sanctions liability is strict: no knowledge or intent is required. Screening depends on name matching against automated onboarding, and beneficial ownership is not consistently established for merchant entities. | Screening against SDN and consolidated lists at onboarding and on each payment; daily list refresh; manual review queue for fuzzy matches; sponsor bank performs independent screening as a second line. | 5 | 3 | 15 | High | Sector data on sanctions screening false negatives; adjusted for automated onboarding volume and incomplete beneficial ownership data. Strict liability means impact does not depend on intent. | Effective | 5 | 2 | 10 | High | 9 | EXCEEDS | Treat | Jonathan Reyes | 31 Mar 2027 | Executive Risk Committee
R-32 | Platform used to launder criminal proceeds | A-01, A-06 | TA-09 | Money launderer (TA-09) | Regulatory compliance | Layering of illicit funds through merchant settlement or loan repayment flows without detection | Transaction monitoring rules were tuned for fraud rather than for laundering typologies. No documented typology coverage assessment. Rapid merchant growth increases the onboarding population faster than review capacity. | Transaction monitoring with alerting; merchant risk scoring at onboarding; enhanced due diligence for high-risk categories; annual independent BSA testing; sponsor bank oversight. | 4 | 4 | 16 | Critical | Onboarding volume growth of 28% year on year against static review capacity; typology coverage unassessed. | Effective | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Jonathan Reyes | 31 Mar 2027 | Executive Risk Committee
R-33 | Suspicious activity report not filed for a reportable cyber-event | Group | TA-10 | Internal process failure (TA-10) | Regulatory compliance | A security incident meeting the SAR filing threshold is handled as a security matter only and the filing obligation is missed | POL-02 section 7 lists regulatory notification obligations and does not include FinCEN SAR filing. There is no defined trigger connecting incident severity to the financial crime team, so the assessment is not made. | SAR process operates for transaction-based suspicion; financial crime team is competent in the obligation; General Counsel determines notification obligations at S1 and S2. | 3 | 4 | 12 | High | Condition present: no trigger exists connecting incident severity to the SAR assessment. Occurrence depends only on an incident meeting the threshold. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Jonathan Reyes | 31 Dec 2026 | CISO
R-34 | Synthetic identity defeats customer identification at borrower onboarding | A-03, A-05 | TA-03 | Lending fraud ring (TA-03) | Regulatory compliance | Fabricated or composite identities pass CIP checks and obtain credit, producing loss and a CIP programme deficiency | Automated decisioning optimises for conversion. Document verification is automated with a manual review threshold that has been raised twice in 18 months to manage volume. | CIP checks against bureau and government data sources; document verification; device and behavioural signals; manual review above a risk threshold; bust-out pattern monitoring in servicing. | 4 | 4 | 16 | Critical | Sector data on synthetic identity in unsecured SME lending; adjusted upward for two increases to the manual review threshold in 18 months. | Effective | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Amara Diallo | 30 Jun 2027 | Executive Risk Committee
R-35 | Sanctions list update is not applied before screening runs | A-01, A-03 | TA-10 | Internal process failure (TA-10) | Regulatory compliance | A newly designated party is screened against a stale list and is not detected | List ingestion is automated but has no monitored failure alert. A silent ingestion failure would not be noticed until the next reconciliation. | Daily automated list refresh; screening at onboarding and per payment; sponsor bank independent screening provides a compensating second line. | 4 | 3 | 12 | High | No monitored alert on ingestion failure; silent failure would persist until reconciliation. | Effective | 3 | 2 | 6 | Moderate | 9 | Within | Treat | Jonathan Reyes | 31 Mar 2027 | CISO
R-36 | Concentration on a single cloud provider with no assessed exit | A-01 to A-07, A-09, A-14, A-15 | TA-10 | Supplier failure (TA-10) | Third-party concentration | Provider-level failure, commercial termination, or regulatory restriction removes the platform on which the entire business operates | One hundred per cent of production runs on AWS. There is no exit assessment, no portability analysis, and no estimate of migration cost or duration. Multi-region is not multi-provider: a provider-level or account-level event affects both regions. | Multi-region architecture within the provider; infrastructure defined as code for 80% of the estate, which would assist portability; enterprise support agreement. | 5 | 2 | 10 | High | L2 reflects the low probability of a provider-level event in any 12-month window. The impact, not the likelihood, drives this risk. | Limited | 5 | 2 | 10 | High | 9 | EXCEEDS | Treat | Marcus Lindqvist | 30 Jun 2027 | Executive Risk Committee
R-37 | Cross-account trust misconfiguration exposes production from a lower environment | A-15, A-01 | TA-08 | Sophisticated attacker (TA-08) | Data confidentiality | An over-permissive IAM role trust policy permits privilege escalation across the account boundary | Account separation is the primary control for environment isolation; a trust policy error would undermine it silently. | Wiz continuous posture monitoring with cross-account path analysis; service control policies at the organisation level; Terraform-managed IAM for the codified estate; quarterly review of cross-account roles. | 5 | 3 | 15 | High | Sector data on cross-account misconfiguration; residual L2 reflects continuous posture monitoring with path analysis. | Effective | 4 | 2 | 8 | Moderate | 9 | Within | Tolerate | Sanjay Mehta | n/a | CISO
R-38 | Loss of the identity provider halts all authenticated access | A-11 | TA-10 | Supplier failure (TA-10) | Service availability | Extended unavailability or compromise of Okta prevents every worker and administrative session from authenticating | Federation to a single identity provider is the intended design and is a deliberate concentration. Break-glass procedures exist for the cloud estate but not for the wider SaaS estate. | Break-glass credentials under dual custody for AWS; provider availability commitment; session persistence limits the immediate blast radius of a short outage. | 5 | 2 | 10 | High | Provider availability history and published incident record for major identity providers. | Limited | 5 | 2 | 10 | High | 9 | EXCEEDS | Treat | Ruth Nakamura | 30 Jun 2027 | Executive Risk Committee
R-39 | Legacy supplier contracts leave Aldridge without enforceable security rights | Supplier estate | TA-10 | Internal process failure (TA-10) | Regulatory compliance | An incident or dispute arises with a supplier whose contract contains no notification, audit, cooperation or data return obligation | Eight Tier 1 and Tier 2 agreements predate the 2023 security schedule, including Northgate Analytics on the payment authorisation path. Aldridge has no contractual remedy and no evidence right. | Confidentiality terms present in all agreements; commercial relationship provides informal leverage; POL-09 applies the current schedule to all new and renewed contracts. | 3 | 4 | 12 | High | Condition present: eight agreements confirmed to lack the security schedule. Likelihood reflects the probability of an incident or dispute arising with one of them. | Limited | 3 | 4 | 12 | High | 9 | EXCEEDS | Treat | Jonathan Reyes | 31 Mar 2027 | Executive Risk Committee
R-40 | Financial failure of a Tier 1 supplier | A-10 | TA-10 | Supplier failure (TA-10) | Third-party concentration | Insolvency or distress at a critical supplier removes the service at short notice | Supplier financial viability is not assessed at onboarding or reassessment. Northgate is a private company whose financial position Aldridge has never reviewed. | Rules-based fallback for fraud decisioning; contractual notice periods; the supplier is established and has an institutional customer base. | 4 | 2 | 8 | Moderate | No financial assessment has been performed, so the estimate is unsupported. This is itself the finding: L2 is a placeholder pending viability review. | Limited | 4 | 2 | 8 | Moderate | 9 | Within | Treat | Elena Petrova | 30 Jun 2027 | CISO
R-41 | Undetected fourth-party concentration across multiple Tier 1 suppliers | Supplier estate | TA-06 | Supply chain (TA-06) | Third-party concentration | Several critical suppliers depend on the same sub-processor, so a single fourth-party failure removes services Aldridge believes to be independent | Sub-processors are not disclosed or mapped (see R-09), so concentration cannot be measured. Aldridge has no portfolio view of its onward supply chain. | None specific. First-tier resilience assessed individually, which does not detect shared dependency. | 4 | 3 | 12 | High | Condition likely present: shared sub-processor use is the norm in SaaS. It cannot be confirmed because the chain is unmapped. | Ineffective | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Elena Petrova | 31 Mar 2027 | Executive Risk Committee
R-42 | Fraud and chargeback losses exceed the provision | A-01 | TA-02 | Payment fraud syndicate (TA-02) | Regulatory compliance | A sustained fraud campaign produces losses beyond the modelled provision, with brand monitoring programme consequences | Fraud decisioning depends on a single external supplier. Loss provisioning is modelled on historic patterns rather than stressed scenarios. | Real-time fraud decisioning; velocity and value limits; chargeback ratio monitoring against brand thresholds; merchant reserve requirements for higher-risk categories. | 4 | 3 | 12 | High | Internal: chargeback ratios tracked monthly and currently within brand thresholds. Likelihood reflects a sustained campaign rather than baseline loss. | Effective | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Oliver Trent | 30 Jun 2027 | CISO
R-43 | Merchant insolvency leaves Aldridge exposed on settled transactions | A-01, A-06 | TA-10 | Non-adversarial (TA-10) | Regulatory compliance | A merchant fails with unfulfilled orders, leaving Aldridge liable for chargebacks it cannot recover | Settlement exposure is a structural feature of acquiring. Merchant credit assessment is performed at onboarding and not consistently refreshed. | Merchant underwriting at onboarding; reserves and delayed settlement for higher-risk categories; exposure monitoring; sponsor bank oversight. | 4 | 3 | 12 | High | Internal: merchant failures occur at low volume annually; exposure has been contained by reserves to date. | Effective | 3 | 3 | 9 | Moderate | 9 | Within | Tolerate | Daniel Okonkwo | n/a | CISO
R-44 | Card testing attack degrades authorisation performance and breaches brand thresholds | A-01, A-10 | TA-02 | Payment fraud syndicate (TA-02) | Service availability | High-volume enumeration of card numbers through merchant checkout inflates authorisation volume and decline ratios | Enumeration is an abuse of legitimate function rather than an intrusion, so intrusion controls do not address it. | Rate limiting at the merchant endpoint; decline ratio monitoring with alerting; fraud decisioning applies velocity rules; brand programme thresholds tracked monthly. | 3 | 4 | 12 | High | Sector data: enumeration attacks against acquiring platforms are frequent. Internal decline ratio monitoring has detected two episodes in 2026. | Effective | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Oliver Trent | 30 Jun 2027 | CISO
R-45 | Data subject access or erasure request cannot be fulfilled within the statutory period | A-05, A-09, A-17 | TA-10 | Internal process failure (TA-10) | Regulatory compliance | A UK data subject request cannot be answered completely because personal data locations are not mapped | The data catalogue covers the CDE and secure data zone. It does not cover the approximately 40 unregistered SaaS applications, collaboration content, or the analytics warehouse in full. | DSAR process operated by the DPO with a one-month statutory clock; search across catalogued systems; legal advice available. | 3 | 4 | 12 | High | Internal: DSAR volume is low but rising. Likelihood reflects the probability that a request touches uncatalogued data. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Sofia Kallio | 31 Mar 2027 | CISO
R-46 | Personal data transferred cross-border without a valid transfer mechanism | A-05 | TA-06 | Supply chain (TA-06) | Regulatory compliance | Data reaches a third country through a supplier arrangement not covered by an assessed transfer mechanism | Northgate performs model training in a US region, disclosed only during the September 2026 assessment. No transfer risk assessment exists for it. The undisclosed fourth-party chain (R-09) may contain further transfers. | Transfer mechanisms documented for known and disclosed flows; DPO reviews new processing arrangements; UK IDTA and SCCs used where applicable. | 3 | 4 | 12 | High | Condition present for the Northgate US processing. Further transfers cannot be excluded pending the R-09 mapping. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Sofia Kallio | 31 Jan 2027 | CISO
R-47 | A breach in unregistered software as a service is not assessed for notification | A-17 | TA-06 | Supply chain (TA-06) | Regulatory compliance | A supplier Aldridge does not know it uses suffers a breach; Aldridge learns of it late or not at all and misses a notification deadline | The approximately 40 unregistered applications have no contract, so no notification obligation binds them, and no owner, so no one is monitoring for their breach disclosures. | None specific until the A.5.23 triage completes. | 3 | 3 | 9 | Moderate | Condition present: 40 applications with no contract and no owner monitoring for disclosure. | Ineffective | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Claire Bennett | 30 Nov 2026 | CISO
R-48 | Certificate or key expiry causes an unplanned production outage | A-01, A-06, A-07 | TA-10 | Internal process failure (TA-10) | Service availability | An expired TLS certificate or rotated key breaks a production integration | The cryptographic key inventory is incomplete and several legacy Aldridge Pay keys have unclear ownership (W-16), so expiry cannot be reliably forecast for those. | Automated certificate management for the codified estate; expiry monitoring and alerting; change freeze discipline around renewals. | 4 | 3 | 12 | High | Internal: two near-miss expiry events in 2026 caught by monitoring, both in the codified estate. The uncodified estate is unmonitored. | Effective | 3 | 2 | 6 | Moderate | 9 | Within | Treat | Sanjay Mehta | 31 Mar 2027 | CISO
R-49 | Sponsor bank restricts or terminates the relationship following a control failure | A-01, Group | TA-10 | Non-adversarial (TA-10) | Regulatory compliance | The partner bank withdraws or restricts sponsorship after an examination finding, a material incident, or a BSA/AML deficiency | The sponsor bank relationship underpins US deposit and settlement operations. There is no assessed alternative sponsor and no estimate of the time required to secure one. | Regular reporting to the sponsor bank; independent BSA testing; strong PCI position; established relationship with no adverse history. | 5 | 2 | 10 | High | No adverse history. L2 reflects the probability of a trigger event severe enough to prompt withdrawal, not the probability of ordinary friction. | Effective | 5 | 2 | 10 | High | 9 | EXCEEDS | Treat | Daniel Okonkwo | 30 Jun 2027 | Executive Risk Committee
R-50 | State money transmitter licence condition imposed following examination | Group | TA-10 | Non-adversarial (TA-10) | Regulatory compliance | A state examination identifies a deficiency resulting in a condition, penalty or licence restriction | Forty-four licences with differing examination cycles and expectations. Evidence production across jurisdictions is manual. | Compliance calendar maintained by Legal; examination preparation process; no adverse findings in the last three cycles. | 5 | 2 | 10 | High | Internal: no adverse findings in the last three examination cycles across the licence portfolio. | Effective | 4 | 2 | 8 | Moderate | 9 | Within | Tolerate | Jonathan Reyes | n/a | CISO
R-51 | The NYDFS Part 500 CISO certification cannot be given truthfully | Group | TA-10 | Internal process failure (TA-10) | Regulatory compliance | The annual certification of compliance to the Superintendent cannot be signed because material programme requirements are unmet | Part 500 requires a documented cybersecurity programme, risk assessment, and specified controls. The gap analysis found 24 of 25 ISO management system requirements unmet, several of which map directly to Part 500 obligations including the risk assessment requirement. | Strong technical controls in access management, encryption and vulnerability management; incident response capability; the certification programme is closing the governance gap. | 4 | 3 | 12 | High | Condition present: the risk assessment and governance requirements underpinning the certification are not yet met. Likelihood reflects whether they close before the certification date. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Helen Achebe-Ward | 31 Jan 2027 | Executive Risk Committee
R-52 | Key person dependency in the uncodified platform estate | A-01, A-02 | TA-10 | Internal process failure (TA-10) | Service availability | Departure of the small number of engineers who understand the semi-manual Aldridge Pay components | Approximately 20% of the Pay estate is not defined as code and is not documented to a standard that would permit another engineer to operate it (W-12). Knowledge is held by three individuals. | Runbooks exist for routine operations; the components are stable; the codification programme will remove the dependency when complete. | 3 | 3 | 9 | Moderate | Internal: knowledge held by three named engineers; departure probability over a 12-month horizon for a group of that size. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Sanjay Mehta | 31 Mar 2027 | CISO
R-53 | Backup restore fails at the point of need for the Credit estate | A-03, A-04, A-05 | TA-10 | Internal process failure (TA-10) | Service availability | A restore is required and fails, or completes outside the recovery objective, because it has never been performed | A full restore of the Aldridge Credit servicing estate has never been performed (W-07). Component-level testing does not validate a full restore of an interdependent estate. | Automated encrypted backups with cross-region replication; component-level restore tested quarterly; backup completion monitored. | 4 | 3 | 12 | High | Internal: full restore never performed. Likelihood reflects the probability of a triggering event combined with untested restore failure rates. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Sanjay Mehta | 31 Mar 2027 | Executive Risk Committee
R-54 | Restricted data submitted to unapproved generative AI tools | A-05, A-13, A-17 | TA-10 | Worker, non-malicious (TA-10) | Data confidentiality | A worker pastes customer data, credit file content or proprietary source code into a consumer AI service to accelerate a task | POL-01 section 3.6 prohibits it and no technical control enforces it. Consumer AI services are reachable from managed endpoints, and several appear in the unregistered application discovery (W-04). Submitted content may be retained and used for training. | POL-01 prohibition; approved tooling register maintained; awareness training covers the topic generically; web gateway blocks a small number of named services. | 4 | 4 | 16 | Critical | Internal: consumer AI services identified in the CASB discovery output. Sector surveys indicate high rates of unsanctioned use. Occurrence is probable and undetected. | Limited | 4 | 3 | 12 | High | 9 | EXCEEDS | Treat | Tomas Vidal | 31 Mar 2027 | Executive Risk Committee
R-55 | Compliance evidence cannot be produced on demand at examination or audit | ISMS | TA-10 | Internal process failure (TA-10) | Regulatory compliance | A regulator, certification body or customer requests evidence that exists but cannot be located, versioned or attested within the time allowed | Policies, exceptions, risks, control evidence and access review records are held across five uncontrolled spreadsheets with no version control or approval record (W-13). | Evidence does substantively exist; the security team can assemble it with effort; PCI evidence production is mature and separately organised. | 3 | 4 | 12 | High | Condition present: five uncontrolled spreadsheets. Likelihood reflects the probability of a demand arriving within the period before the GRC platform is implemented. | Limited | 3 | 3 | 9 | Moderate | 9 | Within | Treat | Chidi Eze | 31 Dec 2026 | CISO

## Risk Treatment Plan
Risk Treatment Plan
Satisfies ISO/IEC 27001 clause 6.1.3(e) and (f). Yellow cells are signature blocks to be completed by the named risk owner.
Risk ID | Risk | Res. rating | Appetite test | Treatment option | Treatment action | Action owner | Target date | Risk owner (accountable executive) | Acceptance authority required | Risk owner approval — signature | Date approved
R-01 | Ransomware encrypts production estate and backups | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sanjay Mehta | 31 Mar 2027 | Sanjay Mehta | Executive Risk Committee
R-02 | Compromise of cloud control-plane credentials | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Sanjay Mehta | n/a | Sanjay Mehta | CISO
R-03 | Cardholder data exfiltrated from the cardholder data environment | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Oliver Trent | n/a | Oliver Trent | CISO
R-04 | Borrower personal data exposed through unregistered software as a service | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Claire Bennett | 30 Nov 2026 | Claire Bennett | Executive Risk Committee
R-05 | Identifiable borrower data retained beyond its lawful retention period | Critical | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Claire Bennett | 31 Mar 2027 | Claire Bennett | Board Audit Committee
R-06 | Malicious activity in Aldridge Credit servicing goes undetected | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Tomas Vidal | 31 Jan 2027 | Tomas Vidal | Executive Risk Committee
R-07 | Compromise of Northgate Analytics exposes data in the authorisation path | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Elena Petrova | 31 Jan 2027 | Elena Petrova | Executive Risk Committee
R-08 | Northgate Analytics outage suspends payment authorisation | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Oliver Trent | 30 Jun 2027 | Oliver Trent | CISO
R-09 | Restricted data resides with undisclosed fourth parties | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Elena Petrova | 31 Mar 2027 | Elena Petrova | Executive Risk Committee
R-10 | Offshore support agent exfiltrates customer data | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Elena Petrova | 31 Mar 2027 | Elena Petrova | Executive Risk Committee
R-11 | Worker credentials phished and used for account takeover | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Ruth Nakamura | n/a | Ruth Nakamura | CISO
R-12 | Untrained population raises susceptibility to social engineering | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Helen Achebe-Ward | 31 Mar 2027 | Helen Achebe-Ward | CISO
R-13 | Unrecorded change to a cardholder data environment component | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sanjay Mehta | 31 Mar 2027 | Sanjay Mehta | Executive Risk Committee
R-14 | Cryptographic key of unclear ownership cannot be rotated during an incident | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sanjay Mehta | 31 Mar 2027 | Sanjay Mehta | Executive Risk Committee
R-15 | Disaster recovery fails to meet stated recovery objectives | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sanjay Mehta | 31 Mar 2027 | Sanjay Mehta | Executive Risk Committee
R-16 | Identifiable production data present in non-production environments | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Amara Diallo | 31 Mar 2027 | Amara Diallo | Executive Risk Committee
R-17 | Design-level security flaw reaches production undetected | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Marcus Lindqvist | 31 Mar 2027 | Marcus Lindqvist | CISO
R-18 | ISO 27001 certification is delayed or fails, costing enterprise revenue | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Helen Achebe-Ward | 31 Jan 2027 | Helen Achebe-Ward | CISO
R-19 | PCI DSS compliance is not sustained at the next assessment | Low | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Oliver Trent | n/a | Oliver Trent | Asset owner
R-20 | Distributed denial of service degrades customer-facing services | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Sanjay Mehta | n/a | Sanjay Mehta | CISO
R-21 | Payment fraud through compromised merchant credentials | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Oliver Trent | 30 Jun 2027 | Oliver Trent | CISO
R-22 | Credit decisioning model produces erroneous or unfair outcomes | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Amara Diallo | n/a | Amara Diallo | CISO
R-23 | Proprietary source code exfiltrated | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Marcus Lindqvist | n/a | Marcus Lindqvist | CISO
R-24 | Compromised software dependency introduces malicious code | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Marcus Lindqvist | 30 Jun 2027 | Marcus Lindqvist | CISO
R-25 | CI/CD pipeline compromise enables unauthorised deployment to production | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Sanjay Mehta | n/a | Sanjay Mehta | CISO
R-26 | London office access cannot be revoked on termination | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Grace Lindberg | 30 Jun 2027 | Grace Lindberg | CISO
R-27 | Loss of the individual holding the risk and compliance record | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Chidi Eze | 31 Dec 2026 | Chidi Eze | CISO
R-28 | Regulatory change outpaces compliance capability | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Jonathan Reyes | n/a | Jonathan Reyes | CISO
R-29 | Targeted intrusion by a well-resourced adversary | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Tomas Vidal | 31 Mar 2027 | Tomas Vidal | Executive Risk Committee
R-30 | Confidential data leaves through endpoint channels not covered by prevention | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Tomas Vidal | 30 Jun 2027 | Tomas Vidal | CISO
R-31 | Sanctioned party onboarded as a merchant or borrower | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Jonathan Reyes | 31 Mar 2027 | Jonathan Reyes | Executive Risk Committee
R-32 | Platform used to launder criminal proceeds | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Jonathan Reyes | 31 Mar 2027 | Jonathan Reyes | Executive Risk Committee
R-33 | Suspicious activity report not filed for a reportable cyber-event | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Jonathan Reyes | 31 Dec 2026 | Jonathan Reyes | CISO
R-34 | Synthetic identity defeats customer identification at borrower onboarding | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Amara Diallo | 30 Jun 2027 | Amara Diallo | Executive Risk Committee
R-35 | Sanctions list update is not applied before screening runs | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Jonathan Reyes | 31 Mar 2027 | Jonathan Reyes | CISO
R-36 | Concentration on a single cloud provider with no assessed exit | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Marcus Lindqvist | 30 Jun 2027 | Marcus Lindqvist | Executive Risk Committee
R-37 | Cross-account trust misconfiguration exposes production from a lower environment | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Sanjay Mehta | n/a | Sanjay Mehta | CISO
R-38 | Loss of the identity provider halts all authenticated access | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Ruth Nakamura | 30 Jun 2027 | Ruth Nakamura | Executive Risk Committee
R-39 | Legacy supplier contracts leave Aldridge without enforceable security rights | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Jonathan Reyes | 31 Mar 2027 | Jonathan Reyes | Executive Risk Committee
R-40 | Financial failure of a Tier 1 supplier | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Elena Petrova | 30 Jun 2027 | Elena Petrova | CISO
R-41 | Undetected fourth-party concentration across multiple Tier 1 suppliers | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Elena Petrova | 31 Mar 2027 | Elena Petrova | Executive Risk Committee
R-42 | Fraud and chargeback losses exceed the provision | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Oliver Trent | 30 Jun 2027 | Oliver Trent | CISO
R-43 | Merchant insolvency leaves Aldridge exposed on settled transactions | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Daniel Okonkwo | n/a | Daniel Okonkwo | CISO
R-44 | Card testing attack degrades authorisation performance and breaches brand thresholds | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Oliver Trent | 30 Jun 2027 | Oliver Trent | CISO
R-45 | Data subject access or erasure request cannot be fulfilled within the statutory period | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sofia Kallio | 31 Mar 2027 | Sofia Kallio | CISO
R-46 | Personal data transferred cross-border without a valid transfer mechanism | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sofia Kallio | 31 Jan 2027 | Sofia Kallio | CISO
R-47 | A breach in unregistered software as a service is not assessed for notification | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Claire Bennett | 30 Nov 2026 | Claire Bennett | CISO
R-48 | Certificate or key expiry causes an unplanned production outage | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sanjay Mehta | 31 Mar 2027 | Sanjay Mehta | CISO
R-49 | Sponsor bank restricts or terminates the relationship following a control failure | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Daniel Okonkwo | 30 Jun 2027 | Daniel Okonkwo | Executive Risk Committee
R-50 | State money transmitter licence condition imposed following examination | Moderate | Within | Tolerate | No further treatment. Existing controls assessed as sufficient; residual accepted at the authority shown. | Jonathan Reyes | n/a | Jonathan Reyes | CISO
R-51 | The NYDFS Part 500 CISO certification cannot be given truthfully | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Helen Achebe-Ward | 31 Jan 2027 | Helen Achebe-Ward | Executive Risk Committee
R-52 | Key person dependency in the uncodified platform estate | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sanjay Mehta | 31 Mar 2027 | Sanjay Mehta | CISO
R-53 | Backup restore fails at the point of need for the Credit estate | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Sanjay Mehta | 31 Mar 2027 | Sanjay Mehta | Executive Risk Committee
R-54 | Restricted data submitted to unapproved generative AI tools | High | EXCEEDS | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Tomas Vidal | 31 Mar 2027 | Tomas Vidal | Executive Risk Committee
R-55 | Compliance evidence cannot be produced on demand at examination or audit | Moderate | Within | Treat | Per remediation actions in AFT-ISMS-GAP-01 and the findings referenced at column Y of the register. Treatment target: residual within the tolerance at column T. | Chidi Eze | 31 Dec 2026 | Chidi Eze | CISO
Clause 6.1.3(f) requires the risk owner to approve the risk treatment plan and to accept the residual information security risk. The signature columns are unsigned. Until they are completed, the ISMS does not satisfy clause 6.1.3 irrespective of the quality of the assessment, and this is a certification-blocking condition. Acceptance authority in column J is the level at which the residual may be accepted per AFT-CTX-01 section 16; it does not replace the risk owner's own approval, which is required in every case.

## Summary & Heat Map
Risk Summary
All counts are formulas driven by the Risk Register tab.
RESIDUAL RISK PROFILE
Rating | Inherent | Residual | Movement
Critical | 13 | 1 | -12
High | 35 | 22 | -13
Moderate | 7 | 31 | 24
Low | 0 | 1 | 1
Total risks | 55
APPETITE AND GOVERNANCE POSITION
Risks exceeding appetite | 23
Risks within appetite | 32
Requiring Board Audit Committee acceptance | 1
Requiring Executive Risk Committee acceptance | 22
Treatment: Treat | 43
Treatment: Tolerate | 12
Risk owner approvals outstanding | 55
RISKS BY THREAT SOURCE
Threat source | Risks | Exceeding appetite
TA-01 — Organised cybercriminal (extortion) | 2 | 1
TA-02 — Payment fraud syndicate | 3 | 0
TA-03 — Lending fraud ring | 1 | 1
TA-04 — Initial access broker / phishing crew | 2 | 0
TA-05 — Malicious or coerced insider | 5 | 2
TA-06 — Supply chain / sub-processor | 6 | 3
TA-07 — Hacktivist / DDoS extortion | 1 | 0
TA-08 — State-aligned actor | 4 | 1
TA-09 — Sanctions evader / money launderer | 2 | 2
TA-10 — Non-adversarial | 29 | 13
RESIDUAL HEAT MAP
Impact ↓ / Likelihood → | L1 | L2 | L3 | L4 | L5
I5 | 2 | 6 | 2 | 0 | 0
I4 | 1 | 5 | 12 | 0 | 1
I3 | 0 | 6 | 17 | 2 | 0
I2 | 0 | 0 | 1 | 0 | 0
I1 | 0 | 0 | 0 | 0 | 0
GOVERNANCE OBSERVATION. A large number of risks sit outside appetite. That is a function of the appetite statement as much as of the control environment: AFT-CTX-01 section 7.4 sets an Averse appetite for both data confidentiality and regulatory compliance, capping acceptable residual at Moderate for the two categories that cover most of the register. An appetite that generates an exceedance list longer than the treatment programme can clear within the year is either aspirational or under-resourced, and the ERC should resolve which. The options are to fund treatment at the level the appetite implies, or to restate the appetite at a level the organisation is actually prepared to operate to. Carrying a permanent exceedance list is the worst of the three, because it normalises operating outside a stated appetite and devalues the escalation it is supposed to trigger.